## Sheet1
Actual Roadmap of the Study Project
| Title | Month
|  | 2019 | [11 empty] | 2020
|  | 4 | M 1 | 5 | 6 | 7 | 8 | M 2 | 9 | 10 | 11 | 12 | M 3 | 1 | 2 | F | 3 | 4
Constant Work
I | Research
II | Documentation
III | Write Report
IV | Organisation and Coordination
1 | Data Collection
1.2 | Evaluation of Software and Machine | SS,RR
1.2 | Collect Asparagus Images
2 | Preprocessing
2.1 | Feature Extraction |  |  | SS, RR, MG
2.2 | Label Application |  |  | MG
2.3 | Create Database |  |  | SS, RR, MG
3 | Labelling
3.1 | Hand-label images for features
3.2 | Dataset creation | [9 empty] | SS, RR, KG
3 | Classification
3.1 | Unsupervised Learning
3.1.1 | Principal Component Analysis | [10 empty] | MS, MB
3.1.2 | Autoencoder | [10 empty] | MG
3.2 | Supervised Learning
3.2.1 | Random Forrest | [10 empty] | KG
3.2.2 | Single-label classification | [10 empty] | JZ, KG
3.2.3 | Multi-label classification | [10 empty] | SS, KG
3.2.4 | Feature Engineering | [10 empty] | MG
3.3 | Semi-supervised Learning
3.3.1 | Variational Autoencoders | [10 empty] | MG
4 | Evaluation
4.1 | Compare Results | [13 empty] | MS, MG
4.2 | Visualize Datasets | [12 empty] | JZ, KG
NO TIME BUFFER
Color Legend
M1 | We get an overview. We know where to start and what to do.
M2 | We are not yet done with the hand-label app and cannot start labelling
the unclassified images yet.
M3 | Our neural networks were not yet running.
Finish | No complete results as of yet.
Comparison of first results of running systems.
Work is done during this period.
Work done by every member of the team